## STATUS UPDATES (hidden)
SUMMARY OF PHASED STATUS REPORT ON ENERGY MANAGEMENT PROJECTS AT BETA HEALTH CARE LIMITED
ANALYSIS OF FINDINGS - STAGE WISE |  |  |  | ANALYSIS OF INVESTMENT AND PAYBACK FUNDAMENTALS
ELEMENT OF INTERVENTION | FINDINGS WITH IMPACT MAPPING |  |  | RECOMMENDATIONS | COST ESTIMATES IN IMPLEMENTATION | ACTUAL QUOTES FOR TOTAL INVESTMENT OUTLAY (during current EMP implementation | FINAL CBA (cost-benefits analysis) and payback period
ENERGY AUDIT | Area | Observations | Root Cause Analysis
| Mains | Voltage drops are high | Contactor settings - CF needs to be >=2.0; lower tratings lead to current leakage around the MCBs and lower induction leading to voltage drops | Reconfiguring the MCB settings and changing the mains MCCB circuitry | 1500000 | 40% OF ESTIMATED PROJECTION | 3690900
|  | CF is high | Quality deficiency in the cables arising from the copper impurities is the prime Cause for the high CF factors | Changing the cables with 40-50% higher current ratings to accommodate for deficient copper purity and consequent prevalence of higher CF factors | 3500000
| Machiney in process lines | Low PF | Motors have developed high impedance factors causing magnetic redundant field | Rewiring with 40% higher rating wirng as per the slot accommodation | 2000000
| Machinery in process lines and AHU | High THD% | Non-linear load application | The PFC bank with harmonic filters that can work as anti-resonants and reduce impedance in the systems | 4000000
| Boilers | High fuel / steam ratio | Inadequate combustioncaused by contaminants in the IDO | Introduction of anti-static additives like the car engine oil to eliminate friction through neutralization of static charges | 127500
SAVINGS DYNAMICS AS PER INVESTMENT PLANS FOR BETA HEALTH CARE (as recommended in the energy audit report) |  | Total Investment | Total kWH savings | Total savings | Payback period in months (investment weighted) | Overall ROI%
|  | 11127500 | 231120 | 3690900 | 39.4283 | 33.17%
|  | SAVINGS ON CURRENT ENERGY | 26.23% | 20.02%
ELEMENT OF INTERVENTION | PERFORMANCE VARIABLE |  | TIMELINE |  | LIKELIHOOD RATING / PROBABILITY |  | GAINS- ASSURED
PROPOSAL COMPONENT | Savings on total energy bill |  | 3 MONTHS |  | 0.9 |  | 10%
| Productivity Enhancement on critical machinery |  |  |  | 0.9 |  | 15%
| Maintenance and repair costs |  |  |  | 0.95 |  | 30%
| Condition based maintenance systems |  |  |  | 0.95 |  | Validation in the process and adapatation in the mainstream activity list
| Integrating the statistical process control models in the SHE accreditation documents for external audits |  |  |  | 0.95
SERVICES PROVIDED HITHERTO | Studies to reconfirm and validate the energy audit findings |  | 2 WEEKS |  | 0.9 |  | THE PROJECTIONS SHALL BE FULFILLED WITH 90% PROBABILITY OF LIKELIHOOD
Clarifying strategies for savings working in energy - with foolproof guarantees
Demonstrated potential thermal energy savings of 25% with productivity enancement possibilites of 20% for granulation and syrup
PROJECTED TIME TO COMPLETE PROPOSED GAINS | Thermal energy optimization - boiler service mechanism |  | 1 WORKING DAY
| Thermal energy optimization - condensate recovery mechanism |  | 5 - 8 WORKING DAYS TO COMMISSION AND REALIZE THE SAVINGS
| Motor rewinding for compression, stirrer motors and low PF elements |  | 1 MONTH TO COMPLETE THE CRITICAL MACHINES
| Rectifiers for THD% controls |  | 6 - 7 WEEKS
| Establishing the statistical models for machinery, electrical and process controls on a multi-domain data |  | 1 MONTH
Establishing the condition based maintenance systems for costs reduction and process efficiency improvements
PROJECTED COSTS TO COMPLETE PROPOSED GAINS | Thermal energy optimization - boiler service mechanism |  | KSH 40,000 / PER YEAR |  | 1 WEEK OWING TO 20% IMPROVEMENTS IN IDO CONSUMPTION
ANALYSIS OF PAYBACK FOR THE EMP PROJECT
| Thermal energy optimization - condensate recovery mechanism |  | KSH 150,000 INCLUSIVE OF FABRICATION, INSTALLATION AND COMMISSIONING |  | 5 WEEKS OWING TO MINIMUM 30% IMPROVEMENTS IN IDO CONSUMPTION
| Motor rewinding for compression, stirrer motors and low PF elements |  | KSH 400,000 FOR THE ENTIRE PLANT |  | 2 MONTHS OWING TO IMPROVED ENERGY BILLS - KPLC
| Rectifiers for THD% controls |  | US $ 20-22k INCLUSIVE OF AIR FREIGHT FOR THE ENTIRE PLANT |  | 6 MONTHS OWING TO LITERALLY ZERO ELECTRICAL BREAKDOWN AND REDUCED ENERGY BILLS
| CADPRESS - MC MECHANICAL OVERHAUL |  | KSH 250,000 |  | 2 WEEKS OWING TO PRODUCTIVITY INCREASE
| Establishing the statistical models for machinery, electrical and process controls on a multi-domain data |  | NA
Establishing the condition based maintenance systems for costs reduction and process efficiency improvements

## THERMAL ENERGY DYNAMICS
THERMAL ENERGY DYNAMICS
Element | Existing State |  |  |  | Post- service optimization |  |  | With condensate recovery
Thermal Energy | With FBD (pre-heating) | With sugar syrup (with pre-heating) | With both (without pre-heating) | With both (pre-heating) | With FBD (with pre-heating) | With sugar syrup (with pre-heating) | With both | With FBD (with pre-heating) | With sugar syrup (with pre-heating) | With both
Boiler pressure | 9 | 8.5 | 2 | 5 | 9.5 | 9.5 | 6 | 9.5 | 9.5 | 7.5
Steam output | 750 | 730-800 | 900 | 850-900 | 600 | 650 | 750 | 450 | 450 | 550
IDO consumption | 66 | 78 |  | 93 | 56 | 64 | 75 | 45 | 50 | 65
Temperature gradient | 50% | 50% | 30% | 40% | 70% | 60% | 50% | 85% | 85% | 65%
Condensate recovery percentage | 42.5% | 42.5% | 25.5% | 34% | 59.5% | 51% | 42.5% | 78.2% | 78.2% | 59.8%
Estimated heat loss % | -57.5% | -57.5% | -74.5% | -66% | -40.5% | -49% | -57.5% | -21.8% | -21.8% | -40.2%
COSTS INVOLVED | VALUES- INVESTMENT | PERIODICITY | SAVINGS DYNAMICS |  | PAYBACK (in months)
Element | Ksh |  | IDO savings | Productivity - batch run time
Servicing the boiler | 40000 | Annual | 50% | 50% | 3
Condensate recovery | 150000
Insulation - LRB | 100000 | Once in 5 years
290000
`

## ELECT.& MECH ENERGY
ELECTRICAL AND MECHANICAL ENERGY DYNAMICS
ACTIVITY MAPPING |  |  |  | COSTS- BENEFITS IMPACT MAPPING |  | PAYBACK DYNAMICS
Identifier | Element | Activity | Activity break down points | Costs in Ksh | Impact | ANALYSIS OF PAY BACK ELEMENTS AFTER IMPLEMENTATION OF A-E PROGRAMS | Elements of payback | Gains% | Payback period in months
A | Motors | Rewinding | 7.5kW - 6 motors (4 compression + stirrer motors for syrup-2 + 15kW - 4 motors (FBD-1, AHU -3) | 400000 | PF |  | Productivity | 15% | 6 months
B | Phase imbalances | Network cable resizing | The actual sizing needs to be verified at site with the site engineer and shall take 2 working days | 2000000 | Drive quality and electrical breakdown + fire hazard |  | Energy bill savings | 10%
C | Machine wiring | Tracing leakage and correcting | Rough estimation | 300000 |  |  | Mechanical breakdown | 70%
D | Harmonics | Correction through rectifiers - Schneider make (ABB make is more expensive and needs negotiation) | Cabling requirements would require a Schneider / ABB engineer to come in and estimate for the factory and shall incur additional costs | 2500000 | Drive quality and electrical + mechanical breakdown |  | Electrical breakdown | 90%
E | Mechanical overhaul | All compression machinery | Suggestion is to go in for the CADPRESS overhaul to begin with before moving on to the other machines after evaluating optimized performances | 1500000 |  |  | Maintenance costs | 30%
|  |  |  | 6700000 | Investment weighted gains% |  |  | 44.33%
ADDITIONAL REMARKS BY THE SERVICE PROVIDER |  |  | 1 | All the productivity, maintenance costs and breakdown gains percentage as projected in the report are dependent on the basic premise of electro-mechanical intervention - the emchanical overhaul is integrated into the initiative for improving on the power quality as a composite.
|  |  | 2 | The motor rewinding, corrections for phase imbalances and the work on the harmonics controls are fundamentally infl;uencing the quality of power - the major determinant for performances of the plant and machinery - none of these lements on a singular mode can make a difference since these interventions are integrated and work together to make the intended differences.
|  |  | 3 | The professional credibility and complete accountability of the service provider goes into providing the performance guarantees that have gone into creating the savings projections. That includes the quality of intervention and achieving the desired results as envisaged in this report.
Note on A7: Author: The actual assessment needs to be done along with the initiatives to resize as well, The phase imbalances are being studied all over again to validate the data and chart the roadmap for the correction.